## Mapping
Month | Quarter | Fiscal Month
1 | 3 | 7
2 | 3 | 8
3 | 3 | 9
4 | 4 | 10
5 | 4 | 11
6 | 4 | 12
7 | 1 | 1
8 | 1 | 2
9 | 1 | 3
10 | 2 | 4
11 | 2 | 5
12 | 2 | 6
Sub Phases
Kick-off
Envisioning
Design
Build
Stabilize
Deploy
Components
All
MWP
Identity
MDC
CyberSecurity
HyperV_VMM
AD_PKI
Exchange
Skype
Hardended_Forest
PAW_Shielded

## Milestone_Status
Milestone Status

## Year_order
All_Billed_Fiscal_year | Year_order
FY19 | 1
FY20 | 2
FY21 | 3
FY22 | 4
FY23 | 5
FY24 | 6
FY25 | 7
Other | 8

## Sub_Phase_order
Sub_Phase_Order | Order
Start | 1
Envisioning | 2
Design | 3
Build | 4
Stabilize | 5
Deploy | 6
Project_1_Amendment | 7

## Forecast_Legends
Forecast Legend | Order
Committed | 1
C@R | 2
Upside | 3
No | 4

## High_level
Year | Quarter | Project | Value_with_Down_Payment | Value_Without_Down_Payment
2019-01-01 | 3 | M | 431600 | 0
2020-07-01 | 1 | M | 287733.334 | 287733.334
2020-10-01 | 2 | M | 359666.667 | 359666.667
2020-01-01 | 3 | M | 470563 | 470563
2021-07-01 | 1 | M | 88963 | 88963
2021-10-01 | 2 | M | 194815 | 194815
2021-01-01 | 3 | M | 116889 | 116889
2021-04-01 | 4 | M | 545482 | 545482
2022-10-01 | 2 | M | 233778 | 233778
2022-01-01 | 3 | M | 311704 | 311704
2022-04-01 | 4 | M | 157926 | 157926
2022-04-01 | 4 | M | 155852 | 155852
2021-10-01 | 2 | P_G | 870000 | 0
2022-07-01 | 1 | P_G | 652500 | 652500
2022-10-01 | 2 | P_G | 217500 | 217500
2022-01-01 | 3 | P_G | 812000 | 812000
2022-04-01 | 4 | P_G | 181250 | 181250
2022-04-01 | 4 | P_G | 167625 | 167625
2022-04-01 | 4 | P_G | 181250 | 181250
2022-04-01 | 4 | P_G | 181250 | 181250

## Main
Milestone | Component | Fee (USD) | Fee (with VAT) | Environment | Phase | Sub Phase | Status | Invoiced Date | Fiscal Year | Fiscal Quarter | Month | Fiscal Month | Milestone Forecasted | Forecast Month | Project | Invoice Number | Down Payment Flag
Upon Start | All | 500000 | 570000 | All | Start | Start | Paid | 2019-03-13 | 2019 | 3 | 3 | 9 | No |  | Project_1 | 9899074736 | Y
Upon Project 1 Envisioning Milestone 1 completion | Env_Comp_1 | 300000 | 342000 | All | Envisioning | Envisioning | Paid | 2019-08-23 | 2020 | 1 | 8 | 2 | No |  | Project_1 | 9899074699 | N
Upon Project 1 Envisioning Milestone 2 completion | Env_Comp_2 | 300000 | 342000 | All | Envisioning | Envisioning | Paid | 2019-08-23 | 2020 | 1 | 8 | 2 | No |  | Project_1 | 9899074699 | N
Upon Project 1 Envisioning Milestone 3 completion | Env_Comp_3 | 300000 | 342000 | All | Envisioning | Envisioning | Paid | 2019-10-30 | 2020 | 2 | 10 | 4 | No |  | Project_1 | 9899074737 | N
Upon Project 1 Design Milestone 1 completion | Design_Comp_1 | 250000 | 285000 | All | Design | Design | Paid | 2020-03-22 | 2020 | 3 | 3 | 9 | No |  | Project_1 | 9899074726 | N
Upon Project 1 Design Milestone 2 completion | Design_Comp_2 | 250000 | 285000 | All | Design | Design | Paid | 2019-11-07 | 2020 | 2 | 11 | 5 | No |  | Project_1 | 9899074730 | N
Upon Project 1 Design Milestone 3 completion | Design_Comp_3 | 250000 | 285000 | All | Design | Design | Paid | 2020-01-17 | 2020 | 3 | 1 | 7 | No |  | Project_1 | 9899074704 | N
Upon Project 1 Phase 1 Milestone 1 Build Completion | Comp1 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-10-22 | 2021 | 2 | 10 | 4 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 2 Build Completion | Comp1 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-03-05 | 2021 | 3 | 3 | 9 | No |  | Project_1 | 9899074733 | N
Upon Project 1 Phase 1 Milestone 1 Stabilize Completion | Comp1 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-11-05 | 2022 | 2 | 11 | 5 | No |  | Project_1 | 9899074721 | N
Upon Project 1 Phase 1 Milestone 2 Stabilize Completion | Comp1 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2022-02-27 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 1 Deploy Completion | Comp1 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-12-28 | 2022 | 2 | 12 | 6 | No |  | Project_1 | 9899074708 | N
Upon Project 1 Phase 1 Milestone 2 Deploy Completion | Comp1 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2022-02-27 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074742 | N
Upon Project 1 Phase 1 Milestone 3 Build Completion | Comp2 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-12-30 | 2021 | 2 | 12 | 6 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 4 Build Completion | Comp2 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-03-11 | 2021 | 3 | 3 | 9 | No |  | Project_1 | 9899074696 | N
Upon Project 1 Phase 1 Milestone 3 Stabilize Completion | Comp2 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Invoiced | 2022-06-01 | 2022 | 4 | 6 | 12 | No |  | Project_1 | 9899074728 | N
Upon Project 1 Phase 1 Milestone 4 Stabilize Completion | Comp2 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Invoiced | 2022-05-30 | 2022 | 4 | 5 | 11 | No |  | Project_1 | 9899074713 | N
Upon Project 1 Phase 1 Milestone 3 Deploy Completion | Comp2 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Invoiced | 2022-06-02 | 2022 | 4 | 6 | 12 | No |  | Project_1 | 9899074708 | N
Upon Project 1 Phase 1 Milestone 4 Deploy Completion | Comp2 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Invoiced | 2022-05-29 | 2022 | 4 | 5 | 11 | No |  | Project_1 | 9899074734 | N
Upon Project 1 Phase 1 Milestone 5 Build Completion | Comp3 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2021-12-29 | 2022 | 2 | 12 | 6 | No |  | Project_1 | 9899074741 | N
Upon Project 1 Phase 1 Milestone 6 Build Completion | Comp3 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-02-26 | 2021 | 3 | 2 | 8 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 5 Stabilize Completion | Comp3 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-05-27 | 2021 | 4 | 5 | 11 | No |  | Project_1 | 9899074696 | N
Upon Project 1 Phase 1 Milestone 6 Stabilize Completion | Comp3 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2021-05-29 | 2021 | 4 | 5 | 11 | No |  | Project_1 | 9899074716 | N
Upon Project 1 Phase 1 Milestone 5 Deploy Completion | Comp3 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-24 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074710 | N
Upon Project 1 Phase 1 Milestone 6 Deploy Completion | Comp3 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2021-06-24 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074700 | N
Upon Project 1 Phase 1 Milestone 7 Build Completion | Comp4 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-11-28 | 2021 | 2 | 11 | 5 | No |  | Project_1 | 9899074718 | N
Upon Project 1 Phase 1 Milestone 8 Build Completion | Comp4 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-05-01 | 2021 | 4 | 5 | 11 | No |  | Project_1 | 9899074734 | N
Upon Project 1 Phase 1 Milestone 7 Stabilize Completion | Comp4 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-07-02 | 2021 | 1 | 7 | 1 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 8 Stabilize Completion | Comp4 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2021-07-01 | 2021 | 1 | 7 | 1 | No |  | Project_1 | 9899074742 | N
Upon Project 1 Phase 1 Milestone 7 Deploy Completion | Comp4 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-30 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074708 | N
Upon Project 1 Phase 1 Milestone 8 Deploy Completion | Comp4 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2021-07-02 | 2021 | 1 | 7 | 1 | No |  | Project_1 | 9899074715 | N
Upon Project 1 Phase 1 Milestone 9 Build Completion | Comp5 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-12-09 | 2021 | 2 | 12 | 6 | No |  | Project_1 | 9899074721 | N
Upon Project 1 Phase 1 Milestone 10 Build Completion | Comp5 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-04-11 | 2021 | 4 | 4 | 10 | No |  | Project_1 | 9899074699 | N
Upon Project 1 Phase 1 Milestone 9 Stabilize Completion | Comp5 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-06-03 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 10 Stabilize Completion | Comp5 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2022-02-14 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074704 | N
Upon Project 1 Phase 1 Milestone 9 Deploy Completion | Comp5 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-25 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074702 | N
Upon Project 1 Phase 1 Milestone 10 Deploy Completion | Comp5 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2022-02-14 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074740 | N
Upon Project 1 Phase 1 Milestone 11 Build Completion | Comp6 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-09-27 | 2021 | 1 | 9 | 3 | No |  | Project_1 | 9899074724 | N
Upon Project 1 Phase 1 Milestone 12 Build Completion | Comp6 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-03-26 | 2021 | 3 | 3 | 9 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 11 Stabilize Completion | Comp6 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2020-02-22 | 2020 | 3 | 2 | 8 | No |  | Project_1 | 9899074726 | N
Upon Project 1 Phase 1 Milestone 12 Stabilize Completion | Comp6 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2022-02-13 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074723 | N
Upon Project 1 Phase 1 Milestone 11 Deploy Completion | Comp6 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-20 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074693 | N
Upon Project 1 Phase 1 Milestone 12 Deploy Completion | Comp6 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2022-02-12 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074721 | N
Upon Project 1 Phase 2 Milestone 1 Build Completion | Comp1 | 200000 | 228000 | Env1 | Phase 2 | Build | Eligible | 2023-06-19 | 2023 | 4 | 6 | 12 | C@R | 3 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 2 Build Completion | Comp1 | 200000 | 228000 | Env2 | Phase 2 | Build | Scheduled | 2023-06-17 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 1 Stabilize Completion | Comp1 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Eligible | 2023-06-19 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 2 Stabilize Completion | Comp1 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Scheduled | 2023-06-22 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 1 Deploy Completion | Comp1 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-12 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 2 Deploy Completion | Comp1 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Scheduled | 2023-06-11 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 3 Build Completion | Comp2 | 200000 | 228000 | Env1 | Phase 2 | Build | WIP | 2023-06-14 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 4 Build Completion | Comp2 | 200000 | 228000 | Env2 | Phase 2 | Build | WIP | 2023-06-20 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 3 Stabilize Completion | Comp2 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | WIP | 2023-06-15 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 4 Stabilize Completion | Comp2 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | WIP | 2023-06-11 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 3 Deploy Completion | Comp2 | 200000 | 228000 | Env1 | Phase 2 | Deploy | WIP | 2023-06-17 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 4 Deploy Completion | Comp2 | 200000 | 228000 | Env2 | Phase 2 | Deploy | WIP | 2023-06-24 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 5 Build Completion | Comp3 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2022-03-03 | 2022 | 3 | 3 | 9 | No |  | Project_1 | 2015700132 | N
Upon Project 1 Phase 2 Milestone 6 Build Completion | Comp3 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-03-10 | 2022 | 3 | 3 | 9 | No |  | Project_1 | 2015700177 | N
Upon Project 1 Phase 2 Milestone 5 Stabilize Completion | Comp3 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Eligible | 2023-06-21 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 6 Stabilize Completion | Comp3 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Eligible | 2023-06-23 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 5 Deploy Completion | Comp3 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-20 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 6 Deploy Completion | Comp3 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Eligible | 2023-06-22 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 7 Build Completion | Comp4 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2021-11-14 | 2022 | 2 | 11 | 5 | No |  | Project_1 | 2015700095 | N
Upon Project 1 Phase 2 Milestone 8 Build Completion | Comp4 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-07-26 | 2022 | 1 | 7 | 1 | No | 1 | Project_1 | 2015700062 | N
Upon Project 1 Phase 2 Milestone 7 Stabilize Completion | Comp4 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Paid | 2021-11-16 | 2022 | 2 | 11 | 5 | No | 0 | Project_1 | 2015700103 | N
Upon Project 1 Phase 2 Milestone 8 Stabilize Completion | Comp4 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | WIP | 2023-06-19 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 7 Deploy Completion | Comp4 | 200000 | 228000 | Env1 | Phase 2 | Deploy | WIP | 2023-06-20 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 8 Deploy Completion | Comp4 | 200000 | 228000 | Env2 | Phase 2 | Deploy | WIP | 2023-06-25 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 9 Build Completion | Comp5 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2021-11-15 | 2022 | 2 | 11 | 5 | No |  | Project_1 | 2015700104 | N
Upon Project 1 Phase 2 Milestone 10 Build Completion | Comp5 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-06-23 | 2022 | 4 | 6 | 12 | No |  | Project_1 | 2015700111 | N
Upon Project 1 Phase 2 Milestone 9 Stabilize Completion | Comp5 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Paid | 2021-06-22 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 2015700096 | N
Upon Project 1 Phase 2 Milestone 10 Stabilize Completion | Comp5 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Eligible | 2023-06-22 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 9 Deploy Completion | Comp5 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-15 | 2023 | 4 | 6 | 12 | No | 0 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 10 Deploy Completion | Comp5 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Eligible | 2023-06-24 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 11 Build Completion | Comp6 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2022-04-03 | 2022 | 4 | 4 | 10 | No |  | Project_1 | 2015700093 | N
Upon Project 1 Phase 2 Milestone 12 Build Completion | Comp6 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-04-03 | 2022 | 4 | 4 | 10 | No |  | Project_1 | 2015700102 | N
Upon Project 1 Phase 2 Milestone 11 Stabilize Completion | Comp6 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Eligible | 2023-06-22 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 12 Stabilize Completion | Comp6 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Eligible | 2023-06-23 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 11 Deploy Completion | Comp6 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-21 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 12 Deploy Completion | Comp6 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Eligible | 2023-06-15 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Amendment start | Ame_All | 200000 | 228000 | Env1 | Amendment | Project_1_Amendment | Paid | 2020-09-26 | 2021 | 1 | 9 | 3 | No |  | Project_1 | 9899173198 | N
Amendment Milestone 1 | Comp1 | 200000 | 228000 | Env2 | Amendment | Project_1_Amendment | Invoiced | 2022-05-03 | 2022 | 4 | 5 | 11 | No |  | Project_1 | 9899173200 | N
Amendment Milestone 2 | Comp1 | 200000 | 228000 | Env1 | Amendment | Project_1_Amendment | WIP | 2023-06-14 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N

## Sub
Milestone | Component | Fee (USD) | Fee (with VAT) | Environment | Phase | Sub Phase | Status
Upon Kick-off | All | 431600 | 492024 | All | Preparation | Preparation | Paid
Upon Identity Envisioning completion | Identity | 143866.667 | 164008.0004 | All | Envisioning | Envisioning | Paid
Upon Cybersecurity Envisioning completion | Cyber Security | 143866.667 | 164008.0004 | All | Envisioning | Envisioning | Paid
Upon Modern Workplace Envisioning completion | MWP | 143866.667 | 164008.0004 | All | Envisioning | Envisioning | Paid
Upon Identity Design completion | Identity | 215800 | 246012 | All | Design | Design | Paid
Upon Cybersecurity Design completion | Cyber Security | 215800 | 246012 | All | Design | Design | Paid
Upon Modern Workplace Design completion | MWP | 215800 | 246012 | All | Design | Design | Paid
Upon AD & PKI & RMS Phase 1 Build - Intranet Completion | AD_PKI_RMS | 38963 | 44417.82 | Intranet | Phase 1 | Build | Paid
Upon AD & PKI & RMS Phase 1 Build - Internet Completion | AD_PKI_RMS | 38963 | 44417.82 | Internet | Phase 1 | Build | Paid
Upon AD & PKI & RMS Phase 1 Stabilize - Intranet Completion | AD_PKI_RMS | 38963 | 44417.82 | Intranet | Phase 1 | Stabilize | Paid
Upon AD & PKI & RMS Phase 1 Stabilize - Internet Completion | AD_PKI_RMS | 38963 | 44417.82 | Internet | Phase 1 | Stabilize | Invoiced
Upon AD & PKI & RMS Phase 1 Deploy - Intranet Completion | AD_PKI_RMS | 38963 | 44417.82 | Intranet | Phase 1 | Deploy | Paid
Upon AD & PKI & RMS Phase 1 Deploy - Internet Completion | AD_PKI_RMS | 38963 | 44417.82 | Internet | Phase 1 | Deploy | Invoiced
Upon MIM & ADFS Phase 1 Build - Intranet Completion | MIM_ADFS | 38963 | 44417.82 | Intranet | Phase 1 | Build | Paid
Upon MIM & ADFS Phase 1 Build - Internet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 1 | Build | Paid
Upon MIM & ADFS Phase 1 Stabilize - Intranet Completion | MIM_ADFS | 38963 | 44417.82 | Intranet | Phase 1 | Stabilize | Scheduled
Upon MIM & ADFS Phase 1 Stabilize - Internet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 1 | Stabilize | Scheduled
Upon MIM & ADFS Phase 1 Deploy - Intranet Completion | MIM_ADFS | 38963 | 44417.82 | Intranet | Phase 1 | Deploy | Scheduled
Upon MIM & ADFS Phase 1 Deploy - Internet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 1 | Deploy | Scheduled
Upon PAW Phase 1 Build - Intranet Completion | PAW | 38963 | 44417.82 | Intranet | Phase 1 | Build | Paid
Upon PAW Phase 1 Build - Internet Completion | PAW | 38963 | 44417.82 | Internet | Phase 1 | Build | Paid
Upon PAW Phase 1 Stabilize - Intranet Completion | PAW | 38963 | 44417.82 | Intranet | Phase 1 | Stabilize | Paid
Upon PAW Phase 1 Stabilize - Internet Completion | PAW | 38963 | 44417.82 | Internet | Phase 1 | Stabilize | Paid
Upon PAW Phase 1 Deploy - Intranet Completion | PAW | 38963 | 44417.82 | Intranet | Phase 1 | Deploy | Paid
Upon PAW Phase 1 Deploy - Internet Completion | PAW | 38963 | 44417.82 | Internet | Phase 1 | Deploy | Paid
Upon ESAE Phase 1 Build - Intranet Completion | ESAE | 38963 | 44417.82 | Intranet | Phase 1 | Build | Paid
Upon ESAE Phase 1 Build - Internet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 1 | Build | Paid
Upon ESAE Phase 1 Stabilize - Intranet Completion | ESAE | 38963 | 44417.82 | Intranet | Phase 1 | Stabilize | Paid
Upon ESAE Phase 1 Stabilize - Internet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 1 | Stabilize | Paid
Upon ESAE Phase 1 Deploy - Intranet Completion | ESAE | 38963 | 44417.82 | Intranet | Phase 1 | Deploy | Paid
Upon ESAE Phase 1 Deploy - Internet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 1 | Deploy | Paid
Upon Exchange Phase 1 Build - Intranet Completion | Exchange | 38963 | 44417.82 | Intranet | Phase 1 | Build | Paid
Upon Exchange Phase 1 Build - Internet Completion | Exchange | 38963 | 44417.82 | Internet | Phase 1 | Build | Paid
Upon Exchange Phase 1 Stabilize - Intranet Completion | Exchange | 38963 | 44417.82 | Intranet | Phase 1 | Stabilize | Paid
Upon Exchange Phase 1 Stabilize - Internet Completion | Exchange | 38963 | 44417.82 | Internet | Phase 1 | Stabilize | Invoiced
Upon Exchange Phase 1 Deploy - Intranet Completion | Exchange | 38963 | 44417.82 | Intranet | Phase 1 | Deploy | Paid
Upon Exchange Phase 1 Deploy - Internet Completion | Exchange | 38963 | 44417.82 | Internet | Phase 1 | Deploy | Invoiced
Upon Skype Phase 1 Build - Intranet Completion | Skype | 38963 | 44417.82 | Intranet | Phase 1 | Build | Paid
Upon Skype Phase 1 Build - Internet Completion | Skpe | 38963 | 44417.82 | Internet | Phase 1 | Build | Paid
Upon Skype Phase 1 Stabilize - Intranet Completion | Skype | 38963 | 44417.82 | Intranet | Phase 1 | Stabilize | Paid
Upon Skype Phase 1 Stabilize - Internet Completion | Skype | 38963 | 44417.82 | Internet | Phase 1 | Stabilize | Invoiced
Upon Skype Phase 1 Deploy - Intranet Completion | Skype | 38963 | 44417.82 | Intranet | Phase 1 | Deploy | Paid
Upon Skype Phase 1 Deploy - Internet Completion | Skype | 38963 | 44417.82 | Internet | Phase 1 | Deploy | Invoiced
Upon AD & PKI & RMS Phase 2 Build - Intranet Completion | AD_PKI_RMS | 38963 | 44417.82 | Intranet | Phase 2 | Build | Scheduled
Upon AD & PKI & RMS Phase 2 Build - Internet Completion | AD_PKI_RMS | 38963 | 44417.82 | Internet | Phase 2 | Build | Scheduled
Upon AD & PKI & RMS Phase 2 Stabilize - Intranet Completion | AD_PKI_RMS | 38963 | 44417.82 | Intranet | Phase 2 | Stabilize | Scheduled
Upon AD & PKI & RMS Phase 2 Stabilize - Internet Completion | AD_PKI_RMS | 38963 | 44417.82 | Internet | Phase 2 | Stabilize | Scheduled
Upon AD & PKI & RMS Phase 2 Deploy - Intranet Completion | AD_PKI_RMS | 38963 | 44417.82 | Intranet | Phase 2 | Deploy | Scheduled
Upon AD & PKI & RMS Phase 2 Deploy - Internet Completion | AD_PKI_RMS | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon MIM & ADFS Phase 2 Build - Intranet Completion | MIM_ADFS | 38963 | 44417.82 | Intranet | Phase 2 | Build | Scheduled
Upon MIM & ADFS Phase 2 Build - Internet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 2 | Build | Scheduled
Upon MIM & ADFS Phase 2 Stabilize - Intranet Completion | MIM_ADFS | 38963 | 44417.82 | Intranet | Phase 2 | Stabilize | Scheduled
Upon MIM & ADFS Phase 2 Stabilize - Internet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 2 | Stabilize | Scheduled
Upon MIM & ADFS Phase 2 Deploy - Intranet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon MIM & ADFS Phase 2 Deploy - Internet Completion | MIM_ADFS | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon ESAE Phase 2 Build - Intranet Completion | ESAE | 38963 | 44417.82 | Intranet | Phase 2 | Build | Invoiced
Upon ESAE Phase 2 Build - Internet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 2 | Build | Invoiced
Upon ESAE Phase 2 Stabilize - Intranet Completion | ESAE | 38963 | 44417.82 | Intranet | Phase 2 | Stabilize | Scheduled
Upon ESAE Phase 2 Stabilize - Internet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 2 | Stabilize | Scheduled
Upon ESAE Phase 2 Deploy - Intranet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon ESAE Phase 2 Deploy - Internet Completion | ESAE | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon Exchange Phase 2 Build - Intranet Completion | Exchange | 38963 | 44417.82 | Intranet | Phase 2 | Build | Paid
Upon Exchange Phase 2 Build - Internet Completion | Exchange | 38963 | 44417.82 | Internet | Phase 2 | Build | Scheduled
Upon Exchange Phase 2 Stabilize - Intranet Completion | Exchange | 38963 | 44417.82 | Intranet | Phase 2 | Stabilize | Paid
Upon Exchange Phase 2 Stabilize - Internet Completion | Exchange | 38963 | 44417.82 | Internet | Phase 2 | Stabilize | Scheduled
Upon Exchange Phase 2 Deploy - Intranet Completion | Exchange | 38963 | 44417.82 | Intranet | Phase 2 | Deploy | Scheduled
Upon Exchange Phase 2 Deploy - Internet Completion | Exchange | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon SharePoint Phase Build - Intranet Completion | SP | 38963 | 44417.82 | Intranet | Phase 2 | Deploy | Paid
Upon SharePoint Phase Build - Internet Completion | SP | 38963 | 44417.82 | Internet | Phase 2 | Build | Scheduled
Upon SharePoint Phase Stabilize - Intranet Completion | SP | 38963 | 44417.82 | Intranet | Phase 2 | Stabilize | Paid
Upon SharePoint Phase Stabilize - Internet Completion | SP | 38963 | 44417.82 | Internet | Phase 2 | Stabilize | Scheduled
Upon SharePoint Phase Deploy - Intranet Completion | SP | 38963 | 44417.82 | Intranet | Phase 2 | Deploy | Scheduled
Upon SharePoint Phase Deploy - Internet Completion | SP | 38963 | 44417.82 | Internet | Phase 2 | Deploy | Scheduled
Upon Skype Phase 2 Build - Intranet Completion | Skype | 38963 | 44417.82 | Intranet | Phase 2 | Build | Invoiced
Upon Skype Phase 2 Build - Internet Completion | Skype | 38963 | 44417.82 | Internet | Phase 2 | Build | Scheduled
Upon Skype Phase 2 Stabilize - Intranet Completion | Skype | 38963 | 44417.82 | Intranet | Phase 2 | Stabilize | Scheduled
Upon Skype Phase 2 Stabilize - Internet Completion | Skype | 38963 | 44417.82 | Internet | Phase 2 | Stabilize | Scheduled
Upon Skype Phase 2 Deploy - Intranet Completion | Skype | 38963 | 44417.82 | Intranet | Phase 2 | Deploy | Scheduled
Upon Skype Phase 2 Deploy - Internet Completion | Skype | 39026.9999 | 44490.7799 | Intranet | Phase 2 | Deploy | Scheduled
Amendment 2 resources mobilization | Ame_All | 50000 | 57000 | Both | Amendment 2 | Amendment 2 | Paid
Amendment 2 MIM Portal Localization | MIM_ADFS | 80000 | 91200 | Both | Amendment 2 | Amendment 2 | Scheduled
Amendment 2 ADFS Localization | MIM_ADFS | 80000 | 91200 | Both | Amendment 2 | Amendment 2 | Scheduled
Total |  | 4526000.0009 |  |  |  |  | 82

## P_G
Milestone | Component | Fee (USD) | Fee (with VAT) | Environment | Sub Phase | Status | Invoiced Date | Fiscal Year | Fiscal Quarter | Month | Fiscal Month | Milestone Forecasted | Forecast Month | Project | Invoice Number | Down Payment Flag
Upon Start | All | 300000 | 342000 | All | Start | Paid | 2020-11-28 | 2021 | 2 | 11 | 5 | No |  | Project_2 | 2015700021 | Y
Upon Project 2 Milestone 1 Vision and Scope acceptance | Env_Comp_1 | 150000 | 171000 | All | Envisioning | Paid | 2021-09-08 | 2022 | 1 | 9 | 3 | No |  | Project_2 | 2015700042 | N
Upon Project 2 Milestone 2 Vision and Scope acceptance | Env_Comp_2 | 150000 | 171000 | All | Envisioning | Paid | 2021-08-29 | 2022 | 1 | 8 | 2 | No |  | Project_2 | 2015700042 | N
Upon Project 2 Milestone 3 Vision and Scope acceptance | Env_Comp_3 | 150000 | 171000 | All | Envisioning | Paid | 2021-11-19 | 2022 | 2 | 11 | 5 | No |  | Project_2 | 2015700054 | N
Upon Project 2 Milestone 4 Vision and Scope acceptance | Env_Comp_4 | 150000 | 171000 | All | Envisioning | Paid | 2021-10-10 | 2022 | 2 | 10 | 4 | No |  | Project_2 | 2015700044 | N
Upon Project 2 Milestone 5 Vision and Scope acceptance | Env_Comp_5 | 150000 | 171000 | All | Envisioning | Paid | 2021-09-06 | 2022 | 1 | 9 | 3 | No |  | Project_2 | 2015700043 | N
Upon Project 2 Milestone 1 Design acceptance | Design_Comp_1 | 100000 | 114000 | All | Design | Invoiced | 2022-06-29 | 2022 | 4 | 6 | 12 | No |  | Project_2 | 2015700103 | N
Upon Project 2 Milestone 2 Design acceptance | Design_Comp_2 | 100000 | 114000 | All | Design | Paid | 2022-02-28 | 2022 | 3 | 2 | 8 | No |  | Project_2 | 2015700072 | N
Upon Project 2 Milestone 3 Design acceptance | Design_Comp_3 | 100000 | 114000 | All | Design | Paid | 2022-03-07 | 2022 | 3 | 3 | 9 | No |  | Project_2 | 2015700076 | N
Upon Project 2 Milestone 4 Design acceptance | Design_Comp_4 | 100000 | 114000 | All | Design | Paid | 2022-03-03 | 2022 | 3 | 3 | 9 | No |  | Project_2 | 2015700068 | N
Upon Project 2 Milestone 1 Build acceptance | Comp1 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-05-28 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700094 | N
Upon Project 2 Milestone 2 Build acceptance | Comp1 | 50000 | 57000 | Env2 | Build | Invoiced | 2022-06-02 | 2022 | 4 | 6 | 12 | No |  | Project_2 | 2015700094 | N
Upon Project 2 Milestone 3 Build acceptance | Comp2 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-06-01 | 2022 | 4 | 6 | 12 | No |  | Project_2 | 2015700101 | N
Upon Project 2 Milestone 4 Build acceptance | Comp2 | 50000 | 57000 | Env2 | Build | Invoiced | 2022-07-08 | 2022 | 1 | 7 | 1 | No |  | Project_2 | 2015700101 | N
Upon Project 2 Milestone 5 Build acceptance | Comp3 | 50000 | 57000 | Env1 | Build | Scheduled | 2023-07-12 | 2023 | 1 | 7 | 1 | C@R | 6 | Project_2 | NA | N
Upon Project 2 Milestone 6 Build acceptance | Comp3 | 50000 | 57000 | Env2 | Build | Scheduled | 2023-07-01 | 2023 | 1 | 7 | 1 | C@R | 6 | Project_2 | NA | N
Upon Project 2 Milestone 7 Build acceptance | Comp4 | 50000 | 57000 | Env1 | Build | WIP | 2023-07-14 | 2023 | 1 | 7 | 1 | Upside | 12 | Project_2 | NA | N
Upon Project 2 Milestone 8 Build acceptance | Comp4 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | Upside | 12 | Project_2 | NA | N
Upon Project 2 Milestone 9 Build acceptance | Comp5 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-05-30 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700089 | N
Upon Project 2 Milestone 10 Build acceptance | Comp5 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-03 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 11 Build acceptance | Comp6 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-05-24 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700088 | N
Upon Project 2 Milestone 12 Build acceptance | Comp6 | 50000 | 57000 | Env2 | Build | Invoiced | 2022-05-31 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700088 | N
Upon Project 2 Milestone 13 Build acceptance | Comp7 | 50000 | 57000 | Env1 | Build | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | C@R | 9 | Project_2 | NA | N
Upon Project 2 Milestone 14 Build acceptance | Comp7 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | Committed | 3 | Project_2 | NA | N
Upon Project 2 Milestone 15 Build acceptance | Comp8 | 50000 | 57000 | Env1 | Build | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 16 Build acceptance | Comp8 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 1 Stabilize acceptance | Comp1 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 2 Stabilize acceptance | Comp1 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 3 Stabilize acceptance | Comp2 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 4 Stabilize acceptance | Comp2 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 5 Stabilize acceptance | Comp3 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 6 Stabilize acceptance | Comp3 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 7 Stabilize acceptance | Comp4 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-14 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 8 Stabilize acceptance | Comp4 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 9 Stabilize acceptance | Comp5 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 10 Stabilize acceptance | Comp5 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-15 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 11 Stabilize acceptance | Comp6 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 12 Build acceptance | Comp6 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 13 Stabilize acceptance | Comp7 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 14 Stabilize acceptance | Comp7 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 15 Stabilize acceptance | Comp8 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 16 Stabilize acceptance | Comp8 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 1 Deploy acceptance | Comp1 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-02 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 2 Deploy acceptance | Comp1 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 3 Deploy acceptance | Comp2 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 4 Deploy acceptance | Comp2 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-15 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 5 Deploy acceptance | Comp3 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 6 Deploy acceptance | Comp3 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-15 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 7 Deploy acceptance | Comp4 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-08 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 8 Deploy acceptance | Comp4 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 9 Deploy acceptance | Comp5 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 10 Deploy acceptance | Comp5 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-08 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 11 Deploy acceptance | Comp6 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 12 Deploy acceptance | Comp6 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 13 Deploy acceptance | Comp7 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 14 Deploy acceptance | Comp7 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 15 Deploy acceptance | Comp8 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 16 Deploy acceptance | Comp8 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N

## DR
Milestone | Component | Planned Date | Fee (USD) | Fee (USD) with VAT | Environment | Sub Phase | Status | Invoiced Date | Milestone Forecasted | Forecast Month | Project | Invoice Number | Down Payment Flag
Upon Kick-off | All | Sunday, May 8, 2022 | 895500 | 1020870 | All | Start | Scheduled | NA | Committed | 3 | DR | NA | Y
Upon Vision and Scope document for AD DS (M-Clouds) acceptance | AD | Tuesday, August 23, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | C@R | 6 | DR | NA | N
Upon Vision and Scope document for AD RMS (M-Clouds) acceptance | ADRMS | Tuesday, August 23, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | C@R | 9 | DR | NA | N
Upon Vision and Scope document for ADFS (M-Clouds) acceptance | ADFS | Tuesday, August 23, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | C@R | 9 | DR | NA | N
Upon Vision and Scope documents for PKI (M-Clouds) acceptance | PKI | Tuesday, August 23, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | Upside | 12 | DR | NA | N
Upon Vision and Scope document for Exchange acceptance | Exchange | Tuesday, October 25, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | C@R | 11 | DR | NA | N
Upon Vision and Scope document for Skype for Business acceptance | Skype | Tuesday, October 25, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | C@R | 11 | DR | NA | N
Upon Vision and Scope document for SharePoint Server acceptance | SP | Tuesday, October 25, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | Upside | 12 | DR | NA | N
Upon Vision and Scope document for Hardened Forest acceptance | Hardended_Forest | Tuesday, November 8, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | Upside | 12 | DR | NA | N
Upon Vision and Scope document for Shielded VMs acceptance | Shielded_VM | Tuesday, November 8, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | Upside | 12 | DR | NA | N
Upon Vision and Scope document for PAW acceptance | PAW | Tuesday, November 8, 2022 | 89550 | 102087 | All | Envisioning | WIP | NA | Upside | 12 | DR | NA | N
Upon design document for AD DS (M-Clouds) acceptance | AD | Tuesday, January 24, 2023 | 119400 | 136116 | All | Design | WIP | NA | Upside | 12 | DR | NA | N
Upon design document for AD RMS (M-Clouds) acceptance | ADRMS | Tuesday, January 24, 2023 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design documents for ADFS (M-Clouds) acceptance | ADFS | Tuesday, January 24, 2023 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design documents for PKI (M-Clouds) acceptance | PKI | Tuesday, January 24, 2023 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design document for Exchange acceptance | Exchange | Sunday, November 27, 2022 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design document for Skype for Business acceptance | Skype | Sunday, November 27, 2022 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design document for SharePoint Server acceptance | SP | Sunday, November 27, 2022 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design document for Hardened Forest acceptance | Hardended_Forest | Sunday, December 11, 2022 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design document for Shielded VMs acceptance | Shielded_VM | Sunday, December 11, 2022 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon design document for PAW acceptance | PAW | Sunday, December 11, 2022 | 119400 | 136116 | All | Design | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Intranet (M cloud) DR Build acceptance | AD | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Internet (M cloud) DR Build acceptance | AD | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Intranet (G cloud) DR Build acceptance | AD | Sunday, June 25, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Internet (P cloud) DR Build acceptance | AD | Sunday, June 25, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Intranet (M cloud) DR Build acceptance | ADFS | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Internet (M cloud) DR Build acceptance | ADFS | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Intranet (G cloud) DR Build acceptance | ADFS | Sunday, June 25, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Internet (P cloud) DR Build acceptance | ADFS | Sunday, June 25, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon PKI Intranet (M cloud) DR Build acceptance | PKI | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon PKI Internet (M cloud) DR Build acceptance | PKI | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon PKI Intranet (G cloud) DR Build acceptance | PKI | Sunday, June 25, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon PKI Internet (P cloud) DR Build acceptance | PKI | Sunday, June 25, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Intranet (M cloud) DR Build acceptance | ADRMS | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Internet (M cloud) DR Build acceptance | ADRMS | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Intranet (G cloud) DR Build acceptance | ADRMS | Sunday, June 25, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Internet (P cloud) DR Build acceptance | ADRMS | Sunday, June 25, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Intranet (M cloud) DR Build acceptance | MIM | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Internet (M cloud) DR Build acceptance | MIM | Sunday, June 25, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Intranet (G cloud) DR Build acceptance | MIM | Sunday, June 25, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Internet (P cloud) DR Build acceptance | MIM | Sunday, June 25, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Intranet ( M cloud) DR Build acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Monday, May 8, 2023 | 18618 | 21224.52 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Internet ( M cloud) DR Build acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Monday, May 8, 2023 | 18618 | 21224.52 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Intranet (G cloud) DR Build acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Monday, May 8, 2023 | 18618 | 21224.52 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Internet ( P cloud) DR Build acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Monday, May 8, 2023 | 18618 | 21224.52 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Intranet (M cloud) DR Build acceptance | Exchange | Thursday, April 27, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Internet (M cloud) DR Build acceptance | Exchange | Thursday, April 27, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Intranet (G cloud) DR Build acceptance | Exchange | Thursday, April 27, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Internet (P cloud) DR Build acceptance | Exchange | Thursday, April 27, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon Skype Intranet (M cloud) DR Build acceptance | Skype | Thursday, April 27, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon Skype Internet (M cloud) DR Build acceptance | Skype | Thursday, April 27, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon Skype Intranet (G cloud) DR Build acceptance | Skype | Thursday, April 27, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon Skype Internet (P cloud) DR Build acceptance | Skype | Thursday, April 27, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon Sharepoint Intranet (M cloud) DR Build acceptance | Sharepoint | Sunday, January 29, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon Sharepoint Internet (M cloud) DR Build acceptance | Sharepoint | Sunday, January 29, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Intranet (M cloud) DR Build acceptance | Hardended_Forest | Tuesday, April 11, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Internet (M cloud) DR Build acceptance | Hardended_Forest | Tuesday, April 11, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Intranet (G cloud) DR Build acceptance | Hardended_Forest | Tuesday, April 11, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Internet (P cloud) DR Build acceptance | Hardended_Forest | Tuesday, April 11, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Intranet (M cloud) DR Build acceptance | Shielded_VM | Tuesday, April 11, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Internet (M cloud) DR Build acceptance | Shielded_VM | Tuesday, April 11, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Intranet (G cloud) DR Build acceptance | Shielded_VM | Tuesday, April 11, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Internet (P cloud) DR Build acceptance | Shielded_VM | Tuesday, April 11, 2023 | 26656 | 30387.84 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Intranet (M cloud) DR Build acceptance | PAW | Tuesday, April 11, 2023 | 26656 | 30387.84 | M_Intra | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Internet (M cloud) DR Build acceptance | PAW | Tuesday, April 11, 2023 | 26656 | 30387.84 | M_Inter | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Intranet (G cloud) DR Build acceptance | PAW | Tuesday, April 11, 2023 | 26656 | 30387.84 | G | Build | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Internet (P cloud) DR Build acceptance | PAW | Tuesday, April 11, 2023 | 26632 | 30360.48 | P | Build | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Intranet (M cloud) DR Stabilize acceptance | AD | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Internet (M cloud) DR Stabilize acceptance | AD | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Intranet (G cloud) DR Stabilize acceptance | AD | Tuesday, July 25, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Internet (P cloud) DR Stabilize acceptance | AD | Tuesday, July 25, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Intranet (M cloud) DR Stabilize acceptance | ADFS | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Internet (M cloud) DR Stabilize acceptance | ADFS | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Intranet (G cloud) DR Stabilize acceptance | ADFS | Tuesday, July 25, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Internet (P cloud) DR Stabilize acceptance | ADFS | Tuesday, July 25, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon PKI Intranet (M cloud) DR Stabilize acceptance | PKI | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon PKI Internet (M cloud) DR Stabilize acceptance | PKI | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon PKI Intranet (G cloud) DR Stabilize acceptance | PKI | Tuesday, July 25, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon PKI Internet (P cloud) DR Stabilize acceptance | PKI | Tuesday, July 25, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Intranet (M cloud) DR Stabilize acceptance | ADRMS | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Internet (M cloud) DR Stabilize acceptance | ADRMS | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Intranet (G cloud) DR Stabilize acceptance | ADRMS | Tuesday, July 25, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Internet (P cloud) DR Stabilize acceptance | ADRMS | Tuesday, July 25, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Intranet (M cloud) DR Stabilize acceptance | MIM | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Internet (M cloud) DR Stabilize acceptance | MIM | Tuesday, July 25, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Intranet (G cloud) DR Stabilize acceptance | MIM | Tuesday, July 25, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Internet (P cloud) DR Stabilize acceptance | MIM | Tuesday, July 25, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Intranet ( M cloud) DR Stabilize acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, September 10, 2023 | 18618 | 21224.52 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Internet ( M cloud) DR Stabilize acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, September 10, 2023 | 18618 | 21224.52 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Intranet (G cloud) DR Stabilize acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, September 10, 2023 | 18618 | 21224.52 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Internet ( P cloud) DR Stabilize acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, September 10, 2023 | 18618 | 21224.52 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Intranet (M cloud) DR Stabilize acceptance | Exchange | Monday, May 29, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Exhange Internet (M cloud) DR Stabilize acceptance | Exchange | Monday, May 29, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Intranet (G cloud) DR Stabilize acceptance | Exchange | Monday, May 29, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Internet (P cloud) DR Stabilize acceptance | Exchange | Monday, May 29, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Skype Intranet (M cloud) DR Stabilize acceptance | Skype | Monday, May 29, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Skype Internet (M cloud) DR Stabilize acceptance | Skype | Monday, May 29, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Skype Intranet (G cloud) DR Stabilize acceptance | Skype | Monday, May 29, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Skype Internet (P cloud) DR Stabilize acceptance | Skype | Monday, May 29, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Sharepoint Intranet (M cloud) DR Stabilize acceptance | Sharepoint | Tuesday, February 28, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon Sharepoint Internet (M cloud) DR Stabilize acceptance | Sharepoint | Tuesday, February 28, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Intranet (M cloud) DR Stabilize acceptance | Hardended_Forest | Thursday, May 11, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Internet (M cloud) DR Stabilize acceptance | Hardended_Forest | Thursday, May 11, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Intranet (G cloud) DR Stabilize acceptance | Hardended_Forest | Thursday, May 11, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Internet (P cloud) DR Stabilize acceptance | Hardended_Forest | Thursday, May 11, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Intranet (M cloud) DR Stabilize acceptance | Shielded_VM | Thursday, May 11, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Internet (M cloud) DR Stabilize acceptance | Shielded_VM | Thursday, May 11, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Intranet (G cloud) DR Stabilize acceptance | Shielded_VM | Thursday, May 11, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Internet (P cloud) DR Stabilize acceptance | Shielded_VM | Thursday, May 11, 2023 | 26656 | 30387.84 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Intranet (M cloud) DR Stabilize acceptance | PAW | Thursday, May 11, 2023 | 26656 | 30387.84 | M_Intra | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Internet (M cloud) DR Stabilize acceptance | PAW | Thursday, May 11, 2023 | 26656 | 30387.84 | M_Inter | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Intranet (G cloud) DR Stabilize acceptance | PAW | Thursday, May 11, 2023 | 26656 | 30387.84 | G | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Internet (P cloud) DR Stabilize acceptance | PAW | Thursday, May 11, 2023 | 26632 | 30360.48 | P | Stabilize | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Intranet (M cloud) DR Deploy acceptance | AD | Monday, November 20, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Internet (M cloud) DR Deploy acceptance | AD | Monday, November 20, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Intranet (G cloud) DR Deploy acceptance | AD | Monday, November 20, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD DS Internet (P cloud) DR Deploy acceptance | AD | Monday, November 20, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Intranet (M cloud) DR Deploy acceptance | ADFS | Monday, November 20, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Internet (M cloud) DR Deploy acceptance | ADFS | Monday, November 20, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Intranet (G cloud) DR Deploy acceptance | ADFS | Monday, November 20, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon ADFS Internet (P cloud) DR Deploy acceptance | ADFS | Monday, November 20, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon PKI Intranet (M cloud) DR Deploy acceptance | PKI | Monday, November 20, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon PKI Internet (M cloud) DR Deploy acceptance | PKI | Monday, November 20, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon PKI Intranet (G cloud) DR Deploy acceptance | PKI | Monday, November 20, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon PKI Internet (P cloud) DR Deploy acceptance | PKI | Monday, November 20, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Intranet (M cloud) DR Deploy acceptance | ADRMS | Monday, November 20, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Internet (M cloud) DR Deploy acceptance | ADRMS | Monday, November 20, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Intranet (G cloud) DR Deploy acceptance | ADRMS | Monday, November 20, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon AD RMS Internet (P cloud) DR Deploy acceptance | ADRMS | Monday, November 20, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Intranet (M cloud) DR Deploy acceptance | MIM | Monday, November 20, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Internet (M cloud) DR Deploy acceptance | MIM | Monday, November 20, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Intranet (G cloud) DR Deploy acceptance | MIM | Monday, November 20, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Identity Management (MIM) Internet (P cloud) DR Deploy acceptance | MIM | Monday, November 20, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Intranet ( M cloud) DR Deploy acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, November 12, 2023 | 18618 | 21224.52 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Internet ( M cloud) DR Deploy acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, November 12, 2023 | 18618 | 21224.52 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Intranet (G cloud) DR Deploy acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, November 12, 2023 | 18618 | 21224.52 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon SQL+HypverV+System Center (SCVMM, SCOM, SCCM) Internet ( P cloud) DR Deploy acceptance | SQL_HypverV_SCVMM_SCOM_SCCM | Sunday, November 12, 2023 | 18618 | 21224.52 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Intranet (M cloud) DR Deploy acceptance | Exchange | Sunday, July 30, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Exhange Internet (M cloud) DR Deploy acceptance | Exchange | Sunday, July 30, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Intranet (G cloud) DR Deploy acceptance | Exchange | Sunday, July 30, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Exchange Internet (P cloud) DR Deploy acceptance | Exchange | Sunday, July 30, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Skype Intranet (M cloud) DR Deploy acceptance | Skype | Sunday, July 30, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Skype Internet (M cloud) DR Deploy acceptance | Skype | Sunday, July 30, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Skype Intranet (G cloud) DR Deploy acceptance | Skype | Sunday, July 30, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Skype Internet (P cloud) DR Deploy acceptance | Skype | Sunday, July 30, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Sharepoint Intranet (M cloud) DR Deploy acceptance | Sharepoint | Sunday, April 30, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon Sharepoint Internet (M cloud) DR Deploy acceptance | Sharepoint | Sunday, April 30, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Intranet (M cloud) DR Deploy acceptance | Hardended_Forest | Sunday, November 12, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Internet (M cloud) DR Deploy acceptance | Hardended_Forest | Sunday, November 12, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Intranet (G cloud) DR Deploy acceptance | Hardended_Forest | Sunday, November 12, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Hardened Forest Internet (P cloud) DR Deploy acceptance | Hardended_Forest | Sunday, November 12, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Intranet (M cloud) DR Deploy acceptance | Shielded_VM | Sunday, November 12, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Internet (M cloud) DR Deploy acceptance | Shielded_VM | Sunday, November 12, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Intranet (G cloud) DR Deploy acceptance | Shielded_VM | Sunday, November 12, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR Shielded VMs Internet (P cloud) DR Deploy acceptance | Shielded_VM | Sunday, November 12, 2023 | 12442 | 14183.88 | P | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Intranet (M cloud) DR Deploy acceptance | PAW | Sunday, November 12, 2023 | 12442 | 14183.88 | M_Intra | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Internet (M cloud) DR Deploy acceptance | PAW | Sunday, November 12, 2023 | 12442 | 14183.88 | M_Inter | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Intranet (G cloud) DR Deploy acceptance | PAW | Sunday, November 12, 2023 | 12442 | 14183.88 | G | Deploy | WIP | NA | No | 0 | DR | NA | N
Upon DR PAW Internet (P cloud) DR Deploy acceptance | PAW | Sunday, November 12, 2023 | 12406 | 14142.84 | P | Deploy | WIP | NA | No | 0 | DR | NA | N