## Mapping
Month | Quarter | Fiscal Month
1 | 3 | 7
2 | 3 | 8
3 | 3 | 9
4 | 4 | 10
5 | 4 | 11
6 | 4 | 12
7 | 1 | 1
8 | 1 | 2
9 | 1 | 3
10 | 2 | 4
11 | 2 | 5
12 | 2 | 6
Sub Phases
Kick-off
Envisioning
Design
Build
Stabilize
Deploy

## Year_order
All_Billed_Fiscal_year | Year_order
FY19 | 1
FY20 | 2
FY21 | 3
FY22 | 4
FY23 | 5
FY24 | 6
FY25 | 7
Other | 8

## Sub_Phase_order
Sub_Phase_Order | Order
Start | 1
Envisioning | 2
Design | 3
Build | 4
Stabilize | 5
Deploy | 6
Project_1_Amendment | 7

## Forecast_Legends
Forecast Legend | Order
Committed | 1
C@R | 2
Upside | 3
No | 4

## Project_1
Milestone | Component | Fee (USD) | Fee (with VAT) | Environment | Phase | Sub Phase | Status | Invoiced Date | Fiscal Year | Fiscal Quarter | Month | Fiscal Month | Milestone Forecasted | Forecast Month | Project | Invoice Number | Down Payment Flag
Upon Start | All | 500000 | 570000 | All | Start | Start | Paid | 2019-03-13 | 2019 | 3 | 3 | 9 | No |  | Project_1 | 9899074736 | Y
Upon Project 1 Envisioning Milestone 1 completion | Env_Comp_1 | 300000 | 342000 | All | Envisioning | Envisioning | Paid | 2019-08-23 | 2020 | 1 | 8 | 2 | No |  | Project_1 | 9899074699 | N
Upon Project 1 Envisioning Milestone 2 completion | Env_Comp_2 | 300000 | 342000 | All | Envisioning | Envisioning | Paid | 2019-08-23 | 2020 | 1 | 8 | 2 | No |  | Project_1 | 9899074699 | N
Upon Project 1 Envisioning Milestone 3 completion | Env_Comp_3 | 300000 | 342000 | All | Envisioning | Envisioning | Paid | 2019-10-30 | 2020 | 2 | 10 | 4 | No |  | Project_1 | 9899074737 | N
Upon Project 1 Design Milestone 1 completion | Design_Comp_1 | 250000 | 285000 | All | Design | Design | Paid | 2020-03-22 | 2020 | 3 | 3 | 9 | No |  | Project_1 | 9899074726 | N
Upon Project 1 Design Milestone 2 completion | Design_Comp_2 | 250000 | 285000 | All | Design | Design | Paid | 2019-11-07 | 2020 | 2 | 11 | 5 | No |  | Project_1 | 9899074730 | N
Upon Project 1 Design Milestone 3 completion | Design_Comp_3 | 250000 | 285000 | All | Design | Design | Paid | 2020-01-17 | 2020 | 3 | 1 | 7 | No |  | Project_1 | 9899074704 | N
Upon Project 1 Phase 1 Milestone 1 Build Completion | Comp1 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-10-22 | 2021 | 2 | 10 | 4 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 2 Build Completion | Comp1 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-03-05 | 2021 | 3 | 3 | 9 | No |  | Project_1 | 9899074733 | N
Upon Project 1 Phase 1 Milestone 1 Stabilize Completion | Comp1 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-11-05 | 2022 | 2 | 11 | 5 | No |  | Project_1 | 9899074721 | N
Upon Project 1 Phase 1 Milestone 2 Stabilize Completion | Comp1 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2022-02-27 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 1 Deploy Completion | Comp1 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-12-28 | 2022 | 2 | 12 | 6 | No |  | Project_1 | 9899074708 | N
Upon Project 1 Phase 1 Milestone 2 Deploy Completion | Comp1 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2022-02-27 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074742 | N
Upon Project 1 Phase 1 Milestone 3 Build Completion | Comp2 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-12-30 | 2021 | 2 | 12 | 6 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 4 Build Completion | Comp2 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-03-11 | 2021 | 3 | 3 | 9 | No |  | Project_1 | 9899074696 | N
Upon Project 1 Phase 1 Milestone 3 Stabilize Completion | Comp2 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Invoiced | 2022-06-01 | 2022 | 4 | 6 | 12 | No |  | Project_1 | 9899074728 | N
Upon Project 1 Phase 1 Milestone 4 Stabilize Completion | Comp2 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Invoiced | 2022-05-30 | 2022 | 4 | 5 | 11 | No |  | Project_1 | 9899074713 | N
Upon Project 1 Phase 1 Milestone 3 Deploy Completion | Comp2 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Invoiced | 2022-06-02 | 2022 | 4 | 6 | 12 | No |  | Project_1 | 9899074708 | N
Upon Project 1 Phase 1 Milestone 4 Deploy Completion | Comp2 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Invoiced | 2022-05-29 | 2022 | 4 | 5 | 11 | No |  | Project_1 | 9899074734 | N
Upon Project 1 Phase 1 Milestone 5 Build Completion | Comp3 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2021-12-29 | 2022 | 2 | 12 | 6 | No |  | Project_1 | 9899074741 | N
Upon Project 1 Phase 1 Milestone 6 Build Completion | Comp3 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-02-26 | 2021 | 3 | 2 | 8 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 5 Stabilize Completion | Comp3 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-05-27 | 2021 | 4 | 5 | 11 | No |  | Project_1 | 9899074696 | N
Upon Project 1 Phase 1 Milestone 6 Stabilize Completion | Comp3 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2021-05-29 | 2021 | 4 | 5 | 11 | No |  | Project_1 | 9899074716 | N
Upon Project 1 Phase 1 Milestone 5 Deploy Completion | Comp3 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-24 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074710 | N
Upon Project 1 Phase 1 Milestone 6 Deploy Completion | Comp3 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2021-06-24 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074700 | N
Upon Project 1 Phase 1 Milestone 7 Build Completion | Comp4 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-11-28 | 2021 | 2 | 11 | 5 | No |  | Project_1 | 9899074718 | N
Upon Project 1 Phase 1 Milestone 8 Build Completion | Comp4 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-05-01 | 2021 | 4 | 5 | 11 | No |  | Project_1 | 9899074734 | N
Upon Project 1 Phase 1 Milestone 7 Stabilize Completion | Comp4 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-07-02 | 2021 | 1 | 7 | 1 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 8 Stabilize Completion | Comp4 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2021-07-01 | 2021 | 1 | 7 | 1 | No |  | Project_1 | 9899074742 | N
Upon Project 1 Phase 1 Milestone 7 Deploy Completion | Comp4 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-30 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074708 | N
Upon Project 1 Phase 1 Milestone 8 Deploy Completion | Comp4 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2021-07-02 | 2021 | 1 | 7 | 1 | No |  | Project_1 | 9899074715 | N
Upon Project 1 Phase 1 Milestone 9 Build Completion | Comp5 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-12-09 | 2021 | 2 | 12 | 6 | No |  | Project_1 | 9899074721 | N
Upon Project 1 Phase 1 Milestone 10 Build Completion | Comp5 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-04-11 | 2021 | 4 | 4 | 10 | No |  | Project_1 | 9899074699 | N
Upon Project 1 Phase 1 Milestone 9 Stabilize Completion | Comp5 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2021-06-03 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 10 Stabilize Completion | Comp5 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2022-02-14 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074704 | N
Upon Project 1 Phase 1 Milestone 9 Deploy Completion | Comp5 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-25 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074702 | N
Upon Project 1 Phase 1 Milestone 10 Deploy Completion | Comp5 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2022-02-14 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074740 | N
Upon Project 1 Phase 1 Milestone 11 Build Completion | Comp6 | 200000 | 228000 | Env1 | Phase 1 | Build | Paid | 2020-09-27 | 2021 | 1 | 9 | 3 | No |  | Project_1 | 9899074724 | N
Upon Project 1 Phase 1 Milestone 12 Build Completion | Comp6 | 200000 | 228000 | Env2 | Phase 1 | Build | Paid | 2021-03-26 | 2021 | 3 | 3 | 9 | No |  | Project_1 | 9899074694 | N
Upon Project 1 Phase 1 Milestone 11 Stabilize Completion | Comp6 | 200000 | 228000 | Env1 | Phase 1 | Stabilize | Paid | 2020-02-22 | 2020 | 3 | 2 | 8 | No |  | Project_1 | 9899074726 | N
Upon Project 1 Phase 1 Milestone 12 Stabilize Completion | Comp6 | 200000 | 228000 | Env2 | Phase 1 | Stabilize | Paid | 2022-02-13 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074723 | N
Upon Project 1 Phase 1 Milestone 11 Deploy Completion | Comp6 | 200000 | 228000 | Env1 | Phase 1 | Deploy | Paid | 2021-06-20 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 9899074693 | N
Upon Project 1 Phase 1 Milestone 12 Deploy Completion | Comp6 | 200000 | 228000 | Env2 | Phase 1 | Deploy | Paid | 2022-02-12 | 2022 | 3 | 2 | 8 | No |  | Project_1 | 9899074721 | N
Upon Project 1 Phase 2 Milestone 1 Build Completion | Comp1 | 200000 | 228000 | Env1 | Phase 2 | Build | Eligible | 2023-06-19 | 2023 | 4 | 6 | 12 | C@R | 3 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 2 Build Completion | Comp1 | 200000 | 228000 | Env2 | Phase 2 | Build | Scheduled | 2023-06-17 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 1 Stabilize Completion | Comp1 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Eligible | 2023-06-19 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 2 Stabilize Completion | Comp1 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Scheduled | 2023-06-22 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 1 Deploy Completion | Comp1 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-12 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 2 Deploy Completion | Comp1 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Scheduled | 2023-06-11 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 3 Build Completion | Comp2 | 200000 | 228000 | Env1 | Phase 2 | Build | WIP | 2023-06-14 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 4 Build Completion | Comp2 | 200000 | 228000 | Env2 | Phase 2 | Build | WIP | 2023-06-20 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 3 Stabilize Completion | Comp2 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | WIP | 2023-06-15 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 4 Stabilize Completion | Comp2 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | WIP | 2023-06-11 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 3 Deploy Completion | Comp2 | 200000 | 228000 | Env1 | Phase 2 | Deploy | WIP | 2023-06-17 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 4 Deploy Completion | Comp2 | 200000 | 228000 | Env2 | Phase 2 | Deploy | WIP | 2023-06-24 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 5 Build Completion | Comp3 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2022-03-03 | 2022 | 3 | 3 | 9 | No |  | Project_1 | 2015700132 | N
Upon Project 1 Phase 2 Milestone 6 Build Completion | Comp3 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-03-10 | 2022 | 3 | 3 | 9 | No |  | Project_1 | 2015700177 | N
Upon Project 1 Phase 2 Milestone 5 Stabilize Completion | Comp3 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Eligible | 2023-06-21 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 6 Stabilize Completion | Comp3 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Eligible | 2023-06-23 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 5 Deploy Completion | Comp3 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-20 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 6 Deploy Completion | Comp3 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Eligible | 2023-06-22 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 7 Build Completion | Comp4 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2021-11-14 | 2022 | 2 | 11 | 5 | No |  | Project_1 | 2015700095 | N
Upon Project 1 Phase 2 Milestone 8 Build Completion | Comp4 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-07-26 | 2022 | 1 | 7 | 1 | No | 1 | Project_1 | 2015700062 | N
Upon Project 1 Phase 2 Milestone 7 Stabilize Completion | Comp4 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Paid | 2021-11-16 | 2022 | 2 | 11 | 5 | No | 0 | Project_1 | 2015700103 | N
Upon Project 1 Phase 2 Milestone 8 Stabilize Completion | Comp4 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | WIP | 2023-06-19 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 7 Deploy Completion | Comp4 | 200000 | 228000 | Env1 | Phase 2 | Deploy | WIP | 2023-06-20 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 8 Deploy Completion | Comp4 | 200000 | 228000 | Env2 | Phase 2 | Deploy | WIP | 2023-06-25 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 9 Build Completion | Comp5 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2021-11-15 | 2022 | 2 | 11 | 5 | No |  | Project_1 | 2015700104 | N
Upon Project 1 Phase 2 Milestone 10 Build Completion | Comp5 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-06-23 | 2022 | 4 | 6 | 12 | No |  | Project_1 | 2015700111 | N
Upon Project 1 Phase 2 Milestone 9 Stabilize Completion | Comp5 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Paid | 2021-06-22 | 2021 | 4 | 6 | 12 | No |  | Project_1 | 2015700096 | N
Upon Project 1 Phase 2 Milestone 10 Stabilize Completion | Comp5 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Eligible | 2023-06-22 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 9 Deploy Completion | Comp5 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-15 | 2023 | 4 | 6 | 12 | No | 0 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 10 Deploy Completion | Comp5 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Eligible | 2023-06-24 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 11 Build Completion | Comp6 | 200000 | 228000 | Env1 | Phase 2 | Build | Paid | 2022-04-03 | 2022 | 4 | 4 | 10 | No |  | Project_1 | 2015700093 | N
Upon Project 1 Phase 2 Milestone 12 Build Completion | Comp6 | 200000 | 228000 | Env2 | Phase 2 | Build | Invoiced | 2022-04-03 | 2022 | 4 | 4 | 10 | No |  | Project_1 | 2015700102 | N
Upon Project 1 Phase 2 Milestone 11 Stabilize Completion | Comp6 | 200000 | 228000 | Env1 | Phase 2 | Stabilize | Eligible | 2023-06-22 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 12 Stabilize Completion | Comp6 | 200000 | 228000 | Env2 | Phase 2 | Stabilize | Eligible | 2023-06-23 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 11 Deploy Completion | Comp6 | 200000 | 228000 | Env1 | Phase 2 | Deploy | Eligible | 2023-06-21 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Upon Project 1 Phase 2 Milestone 12 Deploy Completion | Comp6 | 200000 | 228000 | Env2 | Phase 2 | Deploy | Eligible | 2023-06-15 | 2023 | 4 | 6 | 12 | No |  | Project_1 | NA | N
Amendment start | Ame_All | 200000 | 228000 | Env1 | Amendment | Project_1_Amendment | Paid | 2020-09-26 | 2021 | 1 | 9 | 3 | No |  | Project_1 | 9899173198 | N
Amendment Milestone 1 | Comp1 | 200000 | 228000 | Env2 | Amendment | Project_1_Amendment | Invoiced | 2022-05-03 | 2022 | 4 | 5 | 11 | No |  | Project_1 | 9899173200 | N
Amendment Milestone 2 | Comp1 | 200000 | 228000 | Env1 | Amendment | Project_1_Amendment | WIP | 2023-06-14 | 2023 | 4 | 6 | 12 | C@R | 12 | Project_1 | NA | N

## Project_2
Milestone | Component | Fee (USD) | Fee (with VAT) | Environment | Sub Phase | Status | Invoiced Date | Fiscal Year | Fiscal Quarter | Month | Fiscal Month | Milestone Forecasted | Forecast Month | Project | Invoice Number | Down Payment Flag
Upon Start | All | 300000 | 342000 | All | Start | Paid | 2020-11-28 | 2021 | 2 | 11 | 5 | No |  | Project_2 | 2015700021 | Y
Upon Project 2 Milestone 1 Vision and Scope acceptance | Env_Comp_1 | 150000 | 171000 | All | Envisioning | Paid | 2021-09-08 | 2022 | 1 | 9 | 3 | No |  | Project_2 | 2015700042 | N
Upon Project 2 Milestone 2 Vision and Scope acceptance | Env_Comp_2 | 150000 | 171000 | All | Envisioning | Paid | 2021-08-29 | 2022 | 1 | 8 | 2 | No |  | Project_2 | 2015700042 | N
Upon Project 2 Milestone 3 Vision and Scope acceptance | Env_Comp_3 | 150000 | 171000 | All | Envisioning | Paid | 2021-11-19 | 2022 | 2 | 11 | 5 | No |  | Project_2 | 2015700054 | N
Upon Project 2 Milestone 4 Vision and Scope acceptance | Env_Comp_4 | 150000 | 171000 | All | Envisioning | Paid | 2021-10-10 | 2022 | 2 | 10 | 4 | No |  | Project_2 | 2015700044 | N
Upon Project 2 Milestone 5 Vision and Scope acceptance | Env_Comp_5 | 150000 | 171000 | All | Envisioning | Paid | 2021-09-06 | 2022 | 1 | 9 | 3 | No |  | Project_2 | 2015700043 | N
Upon Project 2 Milestone 1 Design acceptance | Design_Comp_1 | 100000 | 114000 | All | Design | Invoiced | 2022-06-29 | 2022 | 4 | 6 | 12 | No |  | Project_2 | 2015700103 | N
Upon Project 2 Milestone 2 Design acceptance | Design_Comp_2 | 100000 | 114000 | All | Design | Paid | 2022-02-28 | 2022 | 3 | 2 | 8 | No |  | Project_2 | 2015700072 | N
Upon Project 2 Milestone 3 Design acceptance | Design_Comp_3 | 100000 | 114000 | All | Design | Paid | 2022-03-07 | 2022 | 3 | 3 | 9 | No |  | Project_2 | 2015700076 | N
Upon Project 2 Milestone 4 Design acceptance | Design_Comp_4 | 100000 | 114000 | All | Design | Paid | 2022-03-03 | 2022 | 3 | 3 | 9 | No |  | Project_2 | 2015700068 | N
Upon Project 2 Milestone 1 Build acceptance | Comp1 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-05-28 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700094 | N
Upon Project 2 Milestone 2 Build acceptance | Comp1 | 50000 | 57000 | Env2 | Build | Invoiced | 2022-06-02 | 2022 | 4 | 6 | 12 | No |  | Project_2 | 2015700094 | N
Upon Project 2 Milestone 3 Build acceptance | Comp2 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-06-01 | 2022 | 4 | 6 | 12 | No |  | Project_2 | 2015700101 | N
Upon Project 2 Milestone 4 Build acceptance | Comp2 | 50000 | 57000 | Env2 | Build | Invoiced | 2022-07-08 | 2022 | 1 | 7 | 1 | No |  | Project_2 | 2015700101 | N
Upon Project 2 Milestone 5 Build acceptance | Comp3 | 50000 | 57000 | Env1 | Build | Scheduled | 2023-07-12 | 2023 | 1 | 7 | 1 | C@R | 6 | Project_2 | NA | N
Upon Project 2 Milestone 6 Build acceptance | Comp3 | 50000 | 57000 | Env2 | Build | Scheduled | 2023-07-01 | 2023 | 1 | 7 | 1 | C@R | 6 | Project_2 | NA | N
Upon Project 2 Milestone 7 Build acceptance | Comp4 | 50000 | 57000 | Env1 | Build | WIP | 2023-07-14 | 2023 | 1 | 7 | 1 | Upside | 12 | Project_2 | NA | N
Upon Project 2 Milestone 8 Build acceptance | Comp4 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | Upside | 12 | Project_2 | NA | N
Upon Project 2 Milestone 9 Build acceptance | Comp5 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-05-30 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700089 | N
Upon Project 2 Milestone 10 Build acceptance | Comp5 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-03 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 11 Build acceptance | Comp6 | 50000 | 57000 | Env1 | Build | Invoiced | 2022-05-24 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700088 | N
Upon Project 2 Milestone 12 Build acceptance | Comp6 | 50000 | 57000 | Env2 | Build | Invoiced | 2022-05-31 | 2022 | 4 | 5 | 11 | No |  | Project_2 | 2015700088 | N
Upon Project 2 Milestone 13 Build acceptance | Comp7 | 50000 | 57000 | Env1 | Build | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | C@R | 9 | Project_2 | NA | N
Upon Project 2 Milestone 14 Build acceptance | Comp7 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | Committed | 3 | Project_2 | NA | N
Upon Project 2 Milestone 15 Build acceptance | Comp8 | 50000 | 57000 | Env1 | Build | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 16 Build acceptance | Comp8 | 50000 | 57000 | Env2 | Build | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 1 Stabilize acceptance | Comp1 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 2 Stabilize acceptance | Comp1 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 3 Stabilize acceptance | Comp2 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 4 Stabilize acceptance | Comp2 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 5 Stabilize acceptance | Comp3 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 6 Stabilize acceptance | Comp3 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 7 Stabilize acceptance | Comp4 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-14 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 8 Stabilize acceptance | Comp4 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 9 Stabilize acceptance | Comp5 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 10 Stabilize acceptance | Comp5 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-15 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 11 Stabilize acceptance | Comp6 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 12 Build acceptance | Comp6 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 13 Stabilize acceptance | Comp7 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 14 Stabilize acceptance | Comp7 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 15 Stabilize acceptance | Comp8 | 50000 | 57000 | Env1 | Stabilize | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 16 Stabilize acceptance | Comp8 | 50000 | 57000 | Env2 | Stabilize | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 1 Deploy acceptance | Comp1 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-02 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 2 Deploy acceptance | Comp1 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-07 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 3 Deploy acceptance | Comp2 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-04 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 4 Deploy acceptance | Comp2 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-15 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 5 Deploy acceptance | Comp3 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 6 Deploy acceptance | Comp3 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-15 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 7 Deploy acceptance | Comp4 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-08 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 8 Deploy acceptance | Comp4 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-06 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 9 Deploy acceptance | Comp5 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 10 Deploy acceptance | Comp5 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-08 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 11 Deploy acceptance | Comp6 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-13 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 12 Deploy acceptance | Comp6 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-10 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 13 Deploy acceptance | Comp7 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 14 Deploy acceptance | Comp7 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-01 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 15 Deploy acceptance | Comp8 | 50000 | 57000 | Env1 | Deploy | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N
Upon Project 2 Milestone 16 Deploy acceptance | Comp8 | 50000 | 57000 | Env2 | Deploy | WIP | 2023-07-11 | 2023 | 1 | 7 | 1 | No |  | Project_2 | NA | N